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1. Introduction
We are pleased to present the Sharelight Tanzania monthly report for April 2025. This report covers activities conducted under the Sharelight Day & Food Support Project, the Science Vision Camp (SVC) – Phase 4 for 5th class students, and follow-up visits to students who received Horong devices.
2. Sharelight Day
This month’s Sharelight Day was held at the home of Mama Ombeni, one of the beneficiaries of the SaveNeighbour Project. It was a joyful day where participating families came together for a collective cleaning activity. All families attended except that of Pastor Steven, who could not join due to bereavement. We regret to report the passing of Pastor Steven after a short illness involving severe headaches and high blood pressure. His death has deeply saddened all 13 Sharelight partners, who later visited the family to extend their condolences.
As a result, we have planned that the May Sharelight Day will involve all Sharelight staff and partners visiting Pastor Steven’s family to offer their support and sympathy.

3. Food Support Project
We successfully distributed food supplies to all 14 targeted families. The food packages included corn flour (Sembe), dried sardines, and beans. Families who were not present during distribution received their packages through home delivery. All recipients expressed sincere gratitude for the support, and we extend our appreciation to all contributors who made this project possible.
Attached is a link with images documenting the Sharelight Day and Food Support Project.
https://drive.google.com/drive/folders/1XNdQu6wHn25D5m1uODGoA5hgT54ZJ_Zz?usp=sharing

4. Science Vision Camp (SVC) – Phase 4 Completion
The SVC program continued to make a positive impact on the students of Kipera School. The learners showed great enthusiasm and commitment throughout the program. They were attentive in class, actively engaged with the teachers, asked questions when they needed clarification, and responded well during lessons. Attendance was also commendable.
Program Breakdown:
· Week 1: Introduction to SVC, program objectives, Good News session, SVC song, and personal introductions by students and staff.
        https://drive.google.com/drive/folders/1HmrpTWZgew5lmR1lSAHDIni3ZPiYhzvZ?usp=sharing
· Week 2: Deeper understanding of the SVC vision, continued Good News sessions, lessons on basic electricity, and interactive games between students and teachers.
https://drive.google.com/drive/folders/17qcoU5AhgB9NCniNK9DGfvwaufnmY1Y6?usp=sharing
· Week 3: Review of the SVC vision and song, continued Good News sessions, hands-on training in assembling and troubleshooting the Horong device, followed by team-building games.
https://drive.google.com/drive/folders/1jOZQAJemxPT8VY-JkQERKXF1xqCnzQRb?usp=sharing
· Week 4: Final review sessions, Horong device usage, student evaluations, and reflection activities.
https://drive.google.com/drive/folders/1imIANL7UVSPxDNqcqZqffF2Myr9LDK9m?usp=sharing
5. Student Follow-up on Horong Device Usage
We have launched a follow-up initiative to visit all students who received Horong devices upon completion of the four-week SVC program. We began this program in the areas of Mgama and Kipera, with plans to continue weekly visits to Lubungo and Kipera.
Objectives of the follow-up visits include:
1. To ensure students are using the Horong devices effectively.
2. To identify and resolve any challenges they face in using the devices.
3. To build a sustainable relationship with the students and their families.
4. To provide support such as kerosene refills where needed.
5. To gather feedback from users to help improve the design and functionality of our devices.
https://drive.google.com/drive/folders/1hKnPeAvrQe4FZmkH4fnU3NEtAtoSQpHG?usp=sharing
6. Conclusion
On behalf of Sharelight Tanzania, I would like to express our sincere gratitude for the strong collaboration and support we’ve received in carrying out our activities this month. From the Sharelight Day and Food Support Project to the SVC class, we are seeing the positive light of impact especially among the children we serve. The SVC classes, which combine education with fun and interactive learning, continue to give students hope and purpose as they journey toward a brighter future.

Attachments:
· Updated Student List
· Registration Card
· Survey Form







Thank you for your continued support and dedication.
Sincerely,
Joseph Ingaton
Manager, Sharelight Tanzania.
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